## Table 1
Checklist for Safety and Quality Measures at Work Sites
| Name of Inspecting Official with Designation | Name of Site and Location | Date of Inspection
| Sanjay K. Lawhatre CPM/GSU/PUNE | Akurdi
Sno | Compliances | Yes/ No | Remarks
General
1 | Whether complete site inspected from safety point of view? | Yes
2 | Whether the Agency has submitted a detailed work programme of various items of works? 1. Time Schedule (Bar Chart/PERT/CPM) 2. Organisation details(Supervisor/Labour) 3. Plant and Machinery intended to be utilised | YES | Time Schedule (Bar Chart) Organisation details
2a. | Whether Competent Authority has approved the work program submitted by agency? | Yes | approved
3 | Whether Site layout properly marked as per GAD? | Yes
Quality Control
4 | Has the Contractor maintained a proper Quality Control Lab and Testing Facility as per tender condition? | Yes | Conducting cube tests
5 | Has the contractor maintained proper record keeping of Quality control lab? | Yes | maintaining cube registers
6 | Whether valid calibration certificate of all lab equipments available? | N/A | 3rd party inspection
7 | Whether checklist for passing of materials at site is available or not like cement, steel, aggregate, water, welding rods, brick, CC blocks or any other material being used at site? | Yes
8 | Whether method statement has been prepared and followed for each work being executed at site? | Yes
Records and Registers
9 | Whether all mandatory registers are being maintained at site? | Yes | Cube Register, Reinforcement Register, Stock Register, Equipment Register, Slump Test Register, Cement Register,
10 | Whether Register of Registers is being maintained at site? | Yes
11 | Whether labour records are being maintained at site and compliance to labour laws ensured? | Yes
12 | Whether checklist for different component of construction like Crane working, OHE precautions, Temporary works, RCC, Steel work, Stone work, sheetings, brick work, plumbing works, form work, staging etc is being maintained at site ? | Yes
13 | Whether the Contactor has kept one copy of standard specifications, drawings, contract documents etc. at site for ready availability? | Yes
Sno | Compliances | Yes/ No | Remarks
Before Execution
14 | Whether safety arrangement has been checked at site? | Yes
15 | Whether proper Site barricading provided? | Yes
16 | Whether PPE Kits are available? | Yes
17 | Whether double safety harness for working at heights provided to workers? | Yes
18 | While working near tracks , whether Safe distance from track demarcated and staff is aware about it ? | Yes
19 | While working in electrified area whether procedure to maintain safe distance from OHE being followed? | Yes
20 | To check possibility of falling of debris outside barricading - Whether checked and addressed? | Yes
21 | Whether at exacavation location hard barricading is provided or not? | Yes | hard barricading provided
22 | Whether sufficient free space for movement of passenger traffic provided, to avoid any untoward incidents for all works done within station premises, especially on passenger platform? | Yes
23 | Whether to avoid Infringements, SOD checked when working on platform and/or near track? | Yes
24 | Whether proper marking/Barricading with retro-reflective strips being done? | Yes
25 | Whether approval for competent authority has been obtained before proceeding for concreting works ? | Yes
Signage and Warning Boards
26 | Whether the Contractor displayed the details of work through a proper Steel Display Board at the work site? | Yes
27 | Whether caution signages are placed at work site? | Yes
28 | Whether directional signages for alternate space of railway facilities is placed at required location? | Yes
29 | Whether exit signages placed at appropriate location? | Yes
Competency of Workmen at Site
30 | Whether Contractor has engaged competent staff and supervisor as per competence described in contract documents? | Yes
31 | Whether Training imparted to the contractor's supervisor & competency Certificate issued as required in contract documents | N/A
32 | Whether knowledge of men deputed for protection of track/ road along with adequacy of safety equipment. Safety Assurance register being maintained or not? | Yes | Register maintained
Sno | Compliances | Yes/ No | Remarks
33 | Whether tool-box talk for safety councelling of workmen are being followed at site? | Yes
34 | Whether driver of vehicles/machinery briefed about safe working and competency certificate issued? | N/A | Hired Machinery used as required
35 | Whether knowledge of PSSA/ PMS supervisor is checked? | Yes
36 | Whether knowledge of PSSA/ PMS supervisor is found satisfactory? | Yes
37 | Whether knowledge of railway supervisor and staff deputed at site proper and safety assurance being maintained? | Yes
Permissions and Approvals
38 | Whether the Contractor taken permission from Competent Authority for the work to be executed at night? | No | Night work not required and allowed.
39 | Whether permission for any alteration, addition, omission or abandonment of any part of the work , if required has been taken from the competent authority? | Yes
40 | Has the Contractor taken permission of competent authority before blocking, diverting or obstructing any roads or water courses and suitable warning and signage boards provided ? | Yes
41 | Whether launching/de-launching scheme approved by competent authority? | Yes
42 | If explosives are to be used for the works then, has the Contractor obtained permission and necessary licence for the storage and use of explosives? | N/A | Not applicable
43 | Whether other relevant approvals like Tree cutting, Heritage, fire clearances, airport clearance etc have been obtained | Yes
During Execution
44 | Whether the work requires traffic block for execution? | Yes | Block obtain from authority.
45 | Whether block has been obtained and site protected as per GSR and IRPWM? | Yes
46 | Whether Blocks/ Caution order issued for the train drivers in case work is being done near running track? | Yes | only taken blocks
47 | Whether competent look out man deputed by contractor at work site at all hazardous locations ? | Yes
48 | Whether proper temporary support e.g shoring, centering and strutting has been checked and approved for all structures and excavation works? | Yes
49 | Whether stability and safety of all structures , excavation and works has been ensured? | Yes
Sno | Compliances | Yes/ No | Remarks
50 | Whether work is affecting existing structure? If yes, whether method statement is prepared to protect existing structure and approved by competent authority? | Yes
51 | Whether thorough inspection of exisitng structure done and approval of competent authority taken before initiating any work of additional layer on existing structure that increases dead load? | Yes | Conducted load calculation tests and obtained approval from the architect before execution of work.
52 | Whether temporary structure drawings are submitted by the contractor and approved by competent authority? | Yes
53 | Whether temporary work is being executed as per the approved drawing? | Yes
54 | Whether all structural works are being executed as per the approved drawing? | Yes
55 | Whether scaffolds are as per site requirements? | Yes
56 | Whether manufacturer certificate for scaffolding used at site is available? | Yes
57 | Whether Scaffolds are complying to IS 4014 or other applicable standards/specifications as mentioned in the contract documents?
58 | Whether contractor has procured a certificate from the supplier of scaffolding that the tubes, fittings and pre-fabricated frames comply in all respects as per IS 2750, Clause 6.1 and 6.2 or other applicable standards/specifications as mentioned in the contract documents?
59 | Whether the Contractor is maintaining adquate lighting during night working? | N/A | Night work not required and allowed.
60 | Whether cabling work is being done as per approved cable route plan? | Yes
61 | Whether proper precautions have been taken while working near OHE area? | Yes
61a | Whether work permit has been obtained from the competent authority? | Yes
61b | Whether confirmation received from OHE staff regarding OHE discharge before commencemnt of work? | Yes
61c | Whether work is being executed in presence of OHE staff with proper safety gears? | Yes
62 | Whether disturbed track bonds, feeder connection etc have been re- connected properly after completion of work? | Yes | if required.
63 | Whether the earthing/safety arrangements of all the equipment and places which come in direct contact with the passengers including high masts, water coolers, mobile charging points and panels, Distribution Boards etc. ensured? | Yes
Sno | Compliances | Yes/ No | Remarks
64 | Whether it is ensured that there are no open junction boxes as well as exposed or punctured cables at any locations in and around the station premises? | Yes
65 | Whether all loose cables are secured at the worksite? | Yes
66 | Whether the contractor has provided safe and secure access to public premises, streets, throughfare in area affected by the ongoing work? | Yes
Miscellaneous
67 | Whether First-Aid arrangement available at site? | Yes
68 | Whether fire suppresion equipment available at site? | Yes
69 | Whether site power board with requisite IP rating is available? | Yes
70 | Whether list of emergency contact numbers of local Police Stations, Hospitals, Fire Brigade , railway control office, imporatnt official numbers displayed at site office and at prominent locations? | Yes
71 | Has the contractor provided proper facillities for inspection at work site and contractor stores? | Yes
72 | Has the Contractor provided facilities like labour and instruments to Engineers Representatives for checking of all alignments, grades, levels and dimensions? | Yes
73 | Has the contractor provided proper communication system at site? | Yes
74 | Has the contractor indemnified Railway against all losses and damages? | N/A | Not required Yet.
75 | Date of last safety inspection done by Railway supervisor?
76 | Any other items applicable to the site (To be filled by Engineer in- charge) | N/A
* Zonal Railway may expand/modify the checklist with the approval of concerned SAG official
*Zonal Railways to develop supplementary checklists for specific items requiring further detailing