## Slide 1: Status of ROB/RUB (as on 06.01.26) ---CAO/C/RSP

## Slide 2: LC gates elimination-Targetted in 24-25 (RUB -4 nos )
DIV | L-Xing no | Status | TDC
BSL | 129 | Work completed L-xing closed | Commissioned
 | 134 | Box casted,one side Retaining wall comp, otherside 60% done | JAN’26
 | 115A | Box casted,one side Retaining wall comp, otherside 20% done | FEB’26
 | 136 | Box casted.All girder inserted.Box pushing is going to be started. | MAR’26

## Slide 3: Sanctioned works -PH 30 (RSP unit)
Sanctioned year of the works ( umbrella) | Total Nos. of works sanctioned | Cost sharing | Cost (Rs Crore) | Remarks
2015-16 | 1 | 1 | 21.96 Cr Rly & State- 10.98 each | LC 91 –SUR
2019-20 | 4 | 4 | 137.66 Rly & State- 68.83 | LC-281,289, 20 & 32 (NGP)
2020-21 | 23 | 3 | 662.92 | LC-86-BSL 247 &265 –NGP
2021-22 | 15 | 0 | 495.92 | 
2023-24 | 5 | 0 | 191.68 | 
2024-25 | 1 | 0 | 37.00 | 
Total | 49 | 8 | 1547 .14 | 
LC -91 SUR ,281,289,20,32 NGP 3.2.25
20-21 20 on 12.07.24 3 on 3.2.25
21-22,23-24 20 6.08.24

## Slide 4: Sanctioned works -PH 30 (RSP unit)
Division | Total Nos. | Status of GAD |  |  |  |  | Estt |  |  |  | Status of tender |  | 
 |  | Appd | With Div | With state | With CBE | Under pre | Sanctioned | underDiv vetting | Hq fina | Under pre | finalized | opened | Invited
BB | 16 | 11 |  | 2(73&31) | 2(17&34) | 1(54) | 12 | 0 | 1(69) | 3 | 0 | 10 | 0
BSL | 5 | 4 |  | - | - | 1 (80) | 3 | 0 | 1(86 for sending to RB) | 1 | 3 | 0 | 0
NGP | 15 | 7 |  | 1 | - | 7 | 5 | 0 | 2(247 & 265) | 8 | 5 | 0 | 0
Pune | 7 (27 with NHAI) | 4 |  | 2(43, 61diver) | - | 1 | 4 | 0 | 0 | 3 | 0 | 0 | 4
SUR | 4 | 2(42&91) | 1(61) | - | - | 1(40-to be sent to HQ) | 2(40&42) | 1(61) | 0 | 1(91) | 0 | 2 | 0
Total | 47 | 28 | 1 | 5 | 2 | 11 | 26 | 1 | 4 | 16 | 8 | 12 | 4

## Slide 5
Action Plan for balance works including TDC
Division | Total Nos. | Handing over the land | Tender calling | Tender Finalisation | TDC
BB | 16 | 16 (26) | 02( Jan 26) 04 (Feb 26) | 10 (Feb) 02( Mar 26) 04 (Apr 26) | 27-28 3rd quarter-5 nos. - 25,26,27 16 & 18 4th quarter-7 nos- 17,19,20,22,23,34,69 28-29 4th quarter- 4 nos.- 21, 54, 73 &31
BSL | 5 | 5 (26) | 3 (done) 1 (Jan 2026) 1(Feb 2026) | 03 (Finalised) 02 (Mar 2026) | 26-27 4th quarter-2 nos 27-28 1st quarter - 02 nos 3rd quarter - 01 nos.
NGP | 15 | 15 (26) | 5 (done) 2 (Jan 2026) 8 (Feb 2026) | 2 (March 25) 8 (April 2026) | 26-27 4th quarter-5 nos - 258,96, 246,259 & 287 27-28 1st quarter - 02 nos- 247& 265 3rd quarter - 03 nos.,KG-1, 39B, 253 4th quarter-1 nos- 25 28-29 4th quarter- 4 nos.- 20,32,281, 289
PA | 7 | 7 (26) | 4 (Dec 2025) 3 ( Feb 2026) | 4 (Feb 2026) 3 ( April 2026) | 27-28 4th quarter-4 nos -9,10,10A &38 28-29 4th quarter- 3 nos- 4,43 & 61
SUR | 4 | 4 (26) | 2 (done) 1 (Jan2025) 1 ( Feb 2026) | 2 ( Dec 2025) 1 (March 2026) 1 (April 2026) | 27-28 4th quarter-2 nos - 40,42 28-29 4th quarter-2 nos – 61,91

## Slide 6: Target financial yearwise
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
25-26 | 0 | 0 | 0 | 4
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
26-27 | 0 | 0 | 0 | 7
Chart: 27-28
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
27-28 | 2 | 0 | 9 | 14
Chart: 28-29
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
28-29 | 6 | 0 | 7 | 0

## Slide 7: Action plan
Division | Balance GAD |  |  |  | Balance Estt |  |  | Status of balance tender calling | 
 | Balance | Under pre | Agency | Target date of finalisation | Under pre | Target | Remarks | Balance | Target date of calling
BB | 1 | 1 | RITES | 31.01 | 3 | 15.02 | Estt 21 will go to RB | 6 | 3-15.01 3-28.02
BSL | 1 | 1 | CE G | 15.01 | 1 (80) | 20.01 | Estt 86 sent to finance. RB | 2 | 1-15.02 1-31.03
NGP | 7 | 7 | CE G 2 LKT 4 ANAN 1 | 31.01 | 8 | 31.03 | 2 state unwilling to share cost | 10 | 15.01 (2) 15.02 (4) 15.03 (4)
Pune | 1 | 1 | CE G-1 | 31.01 | 3(61,4 & 43) | 31.01 | Estt 4 &43 will go to RB | 3 | 28.02(3)
SUR | 1 | 1 | Shipra-1 | 31.01 | 1(91) | 1- 28.02 | Estt 91 consent of Karnataka govt. required | 2 | 31.01 (1) 31.03(1)
Total | 11 | 11 |  |  | 16 |  |  | 23 | 

## Slide 8: Summary of sanctioned works of PH 30 ( Assigned to RSP unit)
Division | Total Nos. | Land acquisition under special Railway Project ( publication of gazette) |  |  |  | 
 |  | 37A | 7A | 20A (D) | 20E(TDC D+90) | 20F(TDC)(D+180)
 |  | Decl of spl Rly Pro | App of com auth | Intention to acquire land | objections | Final hearing
BB | 16 | 16 | 13 | 3 TDC for 10 -31.01.26 | 10.03.26 | 10.06.26
BSL | 5 | 5 | 4 | 1 TDC for 3- 31.01.26 | 10.03.26 | 10.06.26
NGP | 15 | 15 | 7 | 3 TDC for 4-31.01.26 | 10.03.26 | 10.06.26
Pune | 7 | 7 | 6 | 0 TDC for 6- 31.01.26 | 10.03.26 | 10.06.26
SUR | 4 | 4 | 3 | TDC for 3-31.01.26 | 10.05.26 | 10.07.26
Total | 47 | 47 | 33 | 7 |  | 

## Slide 9: DPR assigned (contract finalized 3.04.25 with DOC 1 YEAR)-PEMS
Division0 | Total Nos. | Drone survey | Alignment and span plan | Finalization of concept plan & GAD | DPR | TDC for Balance work |  |  | Work already shortlisted by HQ on 7.10.25 in 24-25 umbrella
 |  |  |  |  |  | Alignment & span config. | Concept Plan & GAD | DPR | 
BB | 10 | 10 | 9 | 6 | 6 | 20.01. 26 | 23.01. 26 | 25/01/26 | 2(2)
BSL* | 2+2 | 2+2 | 2+0 | 1 | 1 | 15.01. 26 | 19.01. 26 | 25/01/26 | 3(1)
NGP | 05**-1 | 04 | 4 | 3 | 3 | completed | 12.01. 26 | 15/01/26 | 0
Pune | 25 | 25 | 24 | 20 | 20 | 20.01. 26 | 23.01. 26 | 25/01/26 | 7(7)
SUR | 03 | 03 | 3 | 2 | 2 | completed | 12.01. 26 | 15/01/26 | 
Total | 46 | 46 | 42 | 32 | 32 |  |  |  | 12(10#)
*LC 22, Rajkamal (BSL) (7.10.25) has already been shortlisted on 7.10.25. ** LC-39/H does not exist in NGP.
# 5 are in accounts and 5 are for administrative approval due to cost variation.

## Slide 10: Balance DPR (tender opened on 23.12 project consultant)
Division | Total Nos. of ROB’s | Completion period of DPR
BB | 9 | 1 year from award of contract
BSL | 0 | 
NGP | 4 | 
Pune | 8 | 
SUR | 5 | 
Total | 26 | 

## Slide 11: Assistance Required
Filling of vacant post of AEN at Pune and Bhusawal and posting of JAG at BB who is under transfer
Impediments
Utilities shifting within Railways and outside Railways portion- Electrical, S&T and TRD .
In sharing ROBs – non availability of consent by states.